## Slide 1
Project Sponsors:
Autonomous Water Taxi
By: AutoPirates
Date: 19th November 2015
System Engineering: Updates
Team B: Tushar, Shiyu, Bikramjot, Tae-Hyung, William

## Slide 2
Project Updates | Current Status | Updates

## Slide 3
Project Status: Latest Updates | Perception
Tons of data collected for processing
First Field test Successful
Radar data is of good quality so

## Slide 4
Project Status: Latest Updates | Path Planning and Simulation
Created Occupancy Grid Map
Waypoint following tested
Tested STAGE Simulation

## Slide 5
Project Status: WBS Milestones for FVE
Perception
Path Planning
Interface Radar with ROS
10/29
Basic Data Filtering
11/07
Morphological operation
11/14
Contour Extraction
11/18
Object Detection (Boundary box)
11/24
Acquire data using OpenCPN
10/12
Start with overlaying radar data on maps
12/01
Build and explore SBPL
10/26
Generate Occupancy Grid Map
11/10
Test Occupancy Grid Map on STAGE Simulator
11/13
Run planner on OGM to plan the path
11/24
Create waypoint following interface
11/28
Interface with IMU
10/12
Tune motion primitives and OGM
12/02
Tests and Demo’s
PR1
10/15
PR2
10/12
PR3
10/12
PR4
10/12
Field Test1
11/17
FVE
12/03
Finished
Legend
In progress
Not started

## Slide 6
Project Status: Challenges and delays
Path planning needs more efforts to complete tasks before FVE
Shifting one person from perception to path planning
More visits to NREC planned
DELAYS
Navigating through bridges. Radar only gives 2D data
Challenges
Resolution of OGM created from Google Maps is not high

## Slide 7
Updates on Systems Engineering/PM
Radar performance (It was our biggest risk)
RISKS MITIGATED
Navigating the boat under the bridges
RISKS ADDED
Creating OGM from radar data would be challenging and time consuming
No changes in requirements and FVE
Will add a RGB camera. This would be tackled in spring
Add the data of bridges to OGM beforehand
Create our own OGM map using Radar data

## Slide 8
Questions?

## Slide 9
Fall Validation Experiments: Perception
Step ID | Step Description | Success Criteria | Conditions
PE.1 | Start RGB video of field test | This is our ground truth | Location: NSH Demonstration on laptop (Simulation), Projector required
PE.2 | Simultaneously replay and visualize saved raw radar data in ROS | We can see plots of the radar image | 
PE.3 | Show filtered data | The filtered image has less noise than the raw image | 
PE.4 | Demonstrate obstacle detection | Draw bounding box around the obstacles. | 
PE.5 | Show detected objects from radar image while showing recorded video | The radar should detect obstacles that are in the video, at least the boats | 

## Slide 10
Fall Validation Experiments: Path Planning and Simulator
Step ID | Step Description | Success Criteria | Conditions
PL.1 | Interfacing with IMU/GPS | Display logged data from IMU/GPS which we would be collecting during a field test | Location: NSH Demonstration on laptop (Simulation), Projector required
PL.2 | Generate Environment Map | Display occupancy grid map for 2 miles with filled blocks depicting obstacles (For one of the rivers of Pittsburgh) | 
PL.3 | Demonstrate Path Planning | Boat successfully navigates from Point A to Point B in simulator which are 1 mile apart | 
PL.4 | Show obstacle avoidance | Boat successfully avoids obstacles in simulator in the above task. Obstacles are static and are simulated through occupancy grip map |