## Sheet1
S.No | Issue | Solution | Status | Assigned To | Severity | Start Date | End Date
1 | Resolution of google Map is low | Used qGIS and OpenStreet Map | Resolved | Tushar | High | 10-17-2015 | 2015-10-11
2 | SBPL library is throwing some giving unknown exceptions | Enabled debugging by changing config parameters of the library | Resolved | Tushar | High | 10-20-2015 | 10-30-2015
3 | Not able to visualize our Occupancy grid map | Currently using RViz for visualization | Resolved | Tushar | High | 2015-07-11 | 11-20-2015
4 | Slow Radar Filtering | Will look into using OpenCV to implement the filter, and possibly run on the GPU | Pending | William | High | 12-15-2015 | Est: Feb End
5 | Need locations of bridge supports | Will research more map data or public access records | Resolved | Shiyu | High | 12-15-2015 | 01-30-2016
6 | Improve conversion of radar image from polar to cartesian | Low priority, but will need to investigate how the size and scaling affects overall performance | Resolved | Shiyu | Low | 12-15-2015 | 02-15-2016
7 | Determine proper scaling for overlaying radar image onto occupancy grid map | Current implementation is hard-coded for 1 range, will need to investigate further for flexibility | Pending | Bikram | Medium | 12-15-2015 | Est: Feb End
8 | Improve path planning speed | Figure out how to implement a local, tactical planner or speed up the existing global planner | Resolved | Tushar | High | 12-15-2015 | 02-15-2016
9 | More efficient occupancy map representation | Need to research how to better represent a sparse map so that the planner can run faster | Pending | Bikram | Low | 2015-10-12 | Est: Mar Mid
10 | Improve costmap functionality | Incorporate information about obstacle types or regions of the river to influence costing | Pending | Tae-Hyung | Low | 12-15-2015 | Est: Mar End
11 | Re-planning is not working properly | Initial waypoints in the list have to be discarded | Resolved | Tushar | High | 2016-03-02 | 2016-10-02